## SORT BY TASK GROUP
TASK FORCE | TASKS | LINK TO ACTION IN SEED STRATEGY | NEEDS | LEAD FOR TASK | DATE OF COMPLETION | February 2018 Progress
Before the Storm: Need for Seed | Network locally | 3.2.1 |  | All members | May 2017 - April 2018 | Network locally (2017): Office of Policy Analysis Seminar; Mojave National Plant Symposium; Colorado Plateau Native Plant Symposium; Network nationally (2017-2018): Earth Optimism Summit; ASLA; Natural Areas Conference; Society for Range Management
| Network nationally | 3.2.3 | Communication Piece - case studies, id stakeholders, connect to NSS | Peggy Olwell & Sara Oldfield
| Expand Community Wildfire Protection Plan (CWPP) guidance to include plant materials development | Action 3.4.5 |  | Molly Boyter & Josh Stolz
| Case Studies on CO & NY | 3.1.3 &/or 3.3.2 |  | Iain Hyde & Ed Toth
| National Conference Sessions | 4.2.2 | National Adaptation Forum, American Society of Landscape Architects, Society of Ecological Restoration
Communicating the National Seed Strategy | Speak at American Public Gardens Association Conference | 4.2.2 | photos, success stories, seed strategy info | Johnny Randall | 6/19/2017 (to be revised) | Updated Communications Toolbox with new key messages (powerpoint; business cards) ; more updated fact sheets, flyer, and powerpoint need to be uploaded; added; Created invitation-only google drive for access to the large files in the toolbox (https://drive.google.com/drive/folders/0B57dUvPBRVeEejVFM0duMXNrYmM) Developing Speakers Bureau, a list of people familiar with the NSS who could speak are conferences across the country; extended invite; placeholder on PCA website; Poster to be used at conferences is under development (NOTE: BLM has an interactive poster needs updated key messages (https://portals.iucn.org/congress/session/10077) & a another print-ready template)
| Target major conferences and diverse audience and events | Action 4.2.2 | events list, volunteers/speakers | Evelyn Williams
| Develop speakers bureau parameters | Action 4.2.2, Action 4.2.4 | general info, list of speakers, email listserves | Molly McCormick and Elizabeth Rieben
Identification of Federal Seed and Restoration Policy | Develop matrix for inputs | Action 1.1.3 | Compile policy for agencies listed in 1.1.3 of National Seed Strategy - name, link to document, brief summary | Mark Mousseaux, Lillis Urban, Holly Abbandonato, Stephanie Miller, Dirk Netz | week of 7/1/2017 (to be revised) | This group needs to plan its next call and set new completion date. Working on finding a centralized web location to work together remotely.
| Contact agencies and place info in central location | Action 1.1.3, Action 4.2.3
| Conference call to id future actions | Action 1.1.3
Native Plants Support Native Wildlife | Produce a manuscript to provide wildlife biologists and wildlife managers a better understanding of how using locally adapted native plants benefits animal species that are targeted or prioritized for conservation and the need to plan for and address widespread shortages of locally adapted plants | Objective 4.1, various actions under Objective 4.2, and possibly Action 2.4.2 | Contacts with "animal" people Case studies on benefit of using native plants for native animals | Various team members | Fall 2018 | This group needs to plan its next call and set a new completion date. Added some new members to represent the "animal" perspective. Created annotated outline to blockout the elements of the document. Gathering material for case studies.
Public/Private Partnerships | Explore streamlining | Action 1.1.1, Action 1.2.2 | pile of contracts from any agency, work group public and private | Fred Edwards, Rob Wendell, Stacy Johnson, CalLee Davenport, Tom Knezick, Jody Miller | (to be revised) | This group has been inactive; needs to have a call.
| Seed Availability | Action 1.3.1, Action 1.3.2, Action 1.3.3. Action 1.3.4
| Troubleshoot contracts (after action review) | Action 1.3.5
Right Seed Right Place Right Now | Id info hub through initial contact | Action 3.2.1 & 3.2.2 | regional input, small groups, steering committee, ecoregional coordinators | Kevin Gunnell | August 2017 (to be revised) | This group needs to plan its next call and set a new completion date. At last check, Kevin Gunnell has the desire and intent to write up a document/product, but the rest of the group doesn't seem interested.
Seeing is Believing: Demonstration Sites | Develop questions for data call | Action 3.1.2 | questionnaire, promotion through existing sites/Native Seed Network | Carrie Brown with help | February 2018 + (to be adjusted) | Developed a flyer/sign up sheet to use at meetings to let people know of call for info. Developed and disseminated a call for information by email* allowing people to include their projects in the native plant demonstration sites database (*sent over PCA listserve and Native Seed Network)
Data call on existing demonstration sites
team, funding
Identify gaps/develop new sites
Soil Activities under the National Seed Strategy | Interagency Soil Framework ties to NSS | Action 3.4.3, Action 4.2.4 ?2.2.3 & 2.3.4 | think about it | Dave Lindbo | (to be revised) | This group needs to plan its next call and set a new completion date. Had begun identifying NSS links to the Interagency Soil Framework. Began exploring broader connections on regional level and national levels.
| Review NSS and identify soil links | Action 3.4.3 | read it | Greg Eckert
| Compile resources/contacts for assessing soil conditions | Action 3.4.3 | people and time | Greg Eckert
| Identify minimum dataset/indicators for successful restoration | Action 3.4.3, Action 3.4.4, Action 3.4.5 | funding | Leanna VanSlambrook
Tools for Seed Collectors | Communication forum for collectors for 2017 collection season | Action 1.3.2 | platform funding for the long-term | Clara Holmes and Sarah Follett | May 2017 | This group needs to plan its next call and set a new completion date. Created email forum for seed collectors, but attracted few members. Developing "Gap Analysis in Seed Collection" to review publicly available seed data sources like and draft a report.
| Web based portal for location populations, avoiding redundant collections, and holding current collection data | Action 1.3.2, Action 1.3.4 | gap analysis | Michael Way, Sean Hoban, Jessa Davis, Stacy Jacobsen, Meg Engelhardt, Denise Wilson | May 2017
|  | Action 3.2.3 | funding | Kyle Doherty, Stacy Jacobsen, Kerrie Kyde | September 2017
|  | Action 3.2.3 | platform | Melanie Gisler | August 2017 - February 2018
Training Tools for Practitioners, Producers, & Stakeholders on the Use of Native Seed | Produce a report to identify gaps in training courses offered and training needed to increase the understanding of restoration principles and the use of native seed across multiple agencies (Federal, state, tribal, and local), nongovernmental organizations, private sector industries, and universities | Action 3.1.1 | #1 Assess past and current training concerns; Identify gaps and training needs #2 Identify hands-on, more in-depth training needs and funding #3 Consider the need and prospects for a centralized online portal - open/external | Various team members | mid-March 2018 | Developed a call for information to obtain list of currently available training (sent over PCA listserve with a request to share widely). Currently compiling and assessing the materials.
USDA Programs and Native Plants | Develop interested parties list for program proposals | Action 4.2.2 | determine list of producers and outreach (ASTA) | Jane DeMarchi | February 2018 | This group needs to plan its next call and set a new completion date. To date the group had planned to: reach out to state agruiculture departments; connect them with ASTA's native/conservation seed producers; identfy links to and assistance needed from USDA (e.g., tools to grow crops less expensively). Wants to connect with the Public/Private Partnerships group.
| Enhance communication with extension service and ag. research | Objective 4.1 | Id forums for communication and get leadership buy-in | TBD
| Meeting with seed producers and appropriate agency representatives | Action 1.2.2 | Id issues/resources (e.g. consistent demands) | TBD