PRE-VARIANCE PROCESS (Steps A - D)

| √ | Steps/Tasks | General Time Frames | Helpful References |
| --- | --- | --- | --- |
|  | - Encourage optional Pre-Application Meeting. (Not to be confused with the required preliminary application review meetings.) - Discuss areas of interest, application elements, known potential resource conflicts with sensitive resources and values, including special designations or protections, conflicting applications, run through initial screening steps, etc. - Encourage the applicant to review Appendix A of the 2012 Western Solar Plan - Current and Proposed Bureau of Land Management Solar Energy Development Policies and Design Features. - Distribute Attachment 2 – Variance Factors Analysis Report (VFAR) Table of Contents Template. - Distribute Attachment 3 – Factors to be Considered Checklist. - Distribute Solar Plan of Development (POD) Outline. - Share website to the BLM 2012 Western Solar Plan. - Share website to the BLM Land Use Plans. - Encourage a one package application submission to include: Application (Form SF-299), Application Filing Fee, Preliminary POD Draft VFAR, and shapefile data. |  | 43 CFR 2804.10(a) 43 CFR 2804.12(b) IM 2022-027 Western Solar Plan, Volume 1, Section 2.2.2.3.1 (Page 2-44) and Appendix A Preapplication Checklist |
|  | - Receive SF-299 / Variance Application Package. - Evaluate for completeness using IM 2022-027. - If necessary, use a Notice of Deficiency from IM 2022-027 to request any additional application elements such as the application filing fees, Variance Application Package, corporate documents, Preliminary POD, Draft VFAR, etc. Delays in completing the variance application package may extend processing timeframes. |  | 43 CFR 2803.10 43 CFR 2804.12 43 CFR 2804.25 IM 2022-027 |
|  | - Establish L5101 Account. - Setup account according to the checklists found in IM-2022-027 for application filing fee. - Make cost recovery processing determination, notify applicant, and establish cost recovery agreement as appropriate. | Deposit funds within 3 business days of receiving Application Filing Fee. | IM-2022-027 43 CFR 2804.12(b)(4) 43 CFR 2804.14(d) |
|  | - Compile and share for VFAR inclusion. The BLM will compile and share the following with the applicant once BLM has received shapefiles from the applicant, as appropriate: - List of Rights-of-Way (ROW), Leases, or Permits. - Applicants can also gather a list of ROWs, leases, or permits by accessing the BLM LR2000 Reports website. - BLM to use the list to send future adjacent ROW holder notification letters. - List of Mining Claims. - Applicants can also gather a list of Mining Claims by accessing the Minerals and Lands Records System (MLRS) Reports website. - List of Grazing Allotments. - Share with the applicant the 2-year notification requirement. - Applicants can also gather a list of Allotment information by accessing the Rangeland Administration System website. - List of Range Improvements. - Share with the applicant the requirement to compensate for lost range improvements, as applicable. - List of completed cultural inventories and other survey data (if available). | Within 30 calendar days of receiving shapefile. | Adjacent ROW Holder: 43 CFR 2807.14 Mining Claims: 2802 Manual Section .1(2) 2-Year Notification: 43 CFR 4110.4-2(b) Range Improvements: 43 CFR 4120.3-6 |

VARIANCE PROCESS (Steps E - L)

| √ | Steps/Tasks | General Time Frames | Helpful References |
| --- | --- | --- | --- |
|  | - Receive Draft Variance Factors Analysis Report (VFAR). - Evaluate for completeness. - As applicable, the Draft VFAR must cover the primary components provided in the Table of Contents and Factors to be Considered template. - The Draft VFAR should have placeholders for forthcoming information (i.e., application review meetings and public outreach). | Within 14 calendar days from receiving VFAR. | IM 2022-027 |
|  | - Assemble Interdisciplinary Team (IDT) and IDT Review of Draft VFAR. - IDT to pay particular attention to the Factors to be Considered portion of the VFAR. - Remind IDT this is not a NEPA document review. | Allow 14 calendar days for IDT review. |  |
|  | - Schedule Preliminary Application Review Meetings. - Meetings to take place within six months from the time BLM receives the Application Filing Fee. The Authorized Officer retains discretion to determine the structure and attendance of these meetings. - The BLM (w/IDT) and applicant. - Federal and State agencies and local governments. - Sovereign Tribal Nations. - Public outreach. - Any additional meeting as determined appropriate. | Within 45 calendar days from receiving VFAR. | 43 CFR 2804.12(b)(4) Western Solar Plan ROD Section B.5.4 |
|  | - Host required Preliminary Application Review Meetings. - Create a communication strategy to provide attendees with adequate notice and necessary information (i.e., ePlanning, Social Media, etc.). - Provide at least 30 calendar days to allow submission of written comments after each meeting. | Within 180-calendar days (6 months) from receiving the Application Filing Fee. | 43 CFR 2804.12(b)(4) Western Solar Plan, Volume 1, Section 2.2.2.3.1 (Page 2-44 & 2-53) |
|  | - Review Prioritization Criteria (as applicable). - After the meeting have been concluded, the Authorized Officer may reprioritize the project based on information received to date. |  | IM 2022-027 |
|  | - Host VFAR Meeting with Applicant. - The BLM and applicant meet to discuss essential feedback from the meetings to be incorporated into the Final VFAR. - Discuss potential updates to POD and development schedule. | Within 45 calendar days after IDT and Preliminary Application Review Meetings. |  |
|  | - Applicant prepares Final VFAR. - Applicant to revise VFAR based on feedback received from IDT Preliminary Application Review Meetings and Public Outreach. - The applicant may wish to provide updates or changes to the POD and development schedule, as well. |  |  |
|  | - Variance Process Determination. - State Director and local Authorized Officer to decide if the variance package is either: - Favorable – Proceed to Steps M-N. - Unfavorable – Proceed to Step O. | Determination within 30 calendar days of receiving Final VFAR. | 43 CFR 2804.26 IM 2022-027 Western Solar Plan, Volume 1, Section 2.2.2.3.2 (Page 2-55) |

FAVORABLE VARIANCE PACKAGE (Steps M -N)

| √ | Steps/Tasks | General Time Frames | Helpful References |
| --- | --- | --- | --- |
|  | - Prepare Variance Package. - Favorable determinations will include the following for the Variance Package: - Briefing and Information Memorandum (Attachment 4). - Concurrence Memorandum (Attachment 5). - VFAR (Attachment 2 with information from Attachment 3). - Project Map(s) with the site layout. - Project Vicinity Map(s). | Within 30 calendar days from favorable determination. |  |
|  | - Submit Final Variance Package. - Upload Variance Package in the Data Tracking System (DTS) for local routing/surnaming before submitting to BLM Headquarters Renewable Energy Coordination Office (HQ-330). - State Director surnames and submits Variance Package using DTS to the BLM HQ-330 to begin the routing process for Director’s concurrence. - Documents must be uploaded in Word format, except for maps. | Allow 30 calendar days for routing. |  |

UNFAVORABLE VARIANCE PACKAGE (Step O)

| √ | Steps/Tasks | General Time Frames | Helpful References |
| --- | --- | --- | --- |
|  | - Resolve Deficiencies or Deny Application. - Unfavorable determinations by the State Director to include the following options: - State Director and local Authorized Officer to work with the applicant to resolve deficiencies or issue a denial decision with rationale. | Within 15 calendar days from unfavorable determination. |  |